## Slide 1: Government Financial Management Information System (GFMIS)
Abdul Mudabbir Khan
Fiscal Affairs Department, IMF
FAD mission to Iran
Tehran July/August 2015

## Slide 2: Outline of Presentation: Part II
Pitfalls in GFMIS projects
How to guard against pitfalls
Locally developed or commercial off the shelf (COTS) application?
Project management
Costs
Interim system

## Slide 3: Pitfalls in GFMIS projects (1/2)
Lack of Commitment at Cabinet/Minister and/or Department Head level
Inadequate strategic thinking
Inadequate resource allocation
  Financial, human and time
Weak project Management
  Inadequate focus on outputs
  Weak Issues/problem management
  Ineffective risk analysis and management
  Ineffective change management

## Slide 4: Pitfalls in GFMIS projects (2/2)
Inadequate specification and understanding of conceptual design and user requirements
  Over ambitious requirements and unwillingness to compromise (80: 20 rule)
  Changing requirements during the course of the project
Developing in-house systems without necessary expertise
Buying off-the-shelf systems and then doing major customizations
Inadequate and/or ineffective testing

## Slide 5: How to guard against the pitfalls? (1/2)
Think Strategically and resolve big issues
  High level political support
  Objectives
  Scope and coverage
  Other threshold issues
Set up Project Team and Management structure
Develop conceptual model and requirements
Evaluate systems and select the best software for you
  a Rolls Royce may not necessarily be the answer

## Slide 6: How to guard against the pitfalls? (2/2)
Resist changes to agreed requirements
If change is essential, stop implementation, rewrite requirements, reassess whether original approach needs changes
Refuse to be dictated by a moving target

## Slide 7: Locally developed or COTS systems?
Pre 2000, locally developed software (LDSW) were more common
With technological advance, the trend is now towards COTS packages
  Important to avoid/minimize customization of COTS: expensive, difficult to maintain
  COTS may have to be integrated with some LDSW to meet requirements
  80-20 rule
Notes: Commercial off the shelf system (COTS) packages

## Slide 8: Effective Project management is critical
A Steering Committee preferably chaired by the Departmental Secretary or the Minister
A Project Management team chaired by the project manager
Professional project management expertise would be needed

## Slide 9: Typical Project Management Structure
Steering Committee
Project Manager
Budget Team
Treasury Team
ICT Team

## Slide 10: Cost considerations
Scope, coverage, no. of users
Hardware – acquisition and maintenance
Software – initial purchase and recurring costs
Consultancy – conceptual design, functional requirements, IT, testing, training
Other costs – telecommunications, security, back up site etc.

## Slide 11: International experience on costs reflect variations in scope, coverage, efficiencies
Slovak Republic: Total cost $ 60m
Latin America average:$35m - $100m
California: Estimated cost $1.6 billion over 10 years (2008/9 to 2017/18)
  Source: USAID study, which suggests as a broad guide total cost of a GFMIS as US$6 per capita
WB study finds lower costs
  49 operational systems: $6.6m (average cost)
  32 active projects: $12.6M (average cost)
  Russian Federation: $576m (outlier in WB sample)

## Slide 12: Other key Implementation issues
Customization
Configuration
Testing
Pilot implementation
Full implementation

## Slide 13: User acceptance testing (UAT)
You cannot over test
User must take ownership of testing
Preferably have a company independent of the software vendor helping you with the testing

## Slide 14: Pilot
Often a good idea
Involves running the system in a few locations for brief period while also running the old system
Evaluate the pilot
Reconfigure and retest as necessary

## Slide 15
Conceptual Model
Legal and Institutional changes
Technical Design
Systems Procurement
Customization
Pilot Systems Implementation
Systems Replication
Change Management & End User Training
12-18months
12-18 months
24-36 months
Indicative Implementation Schedule

## Slide 16: Finally…..
GFMIS is probably the most resource intensive, time consuming and complex project MoF will undertake
  Important to have realistic budgets, timetable, and project management
Clarify exactly what the GFMIS is required to do – be realistic
You cannot do too much testing
Do not forget change management

## Slide 17: Issues for discussion..
What kind of GFMIS exists now?
  Are there issues with the system?
What improvements are required and does the treasury modernization initiative intend to implement these?
With current institutional arrangements how can budget and treasury systems communicate better?
  Are there plans to integrate the systems?

## Slide 18: References
Dener, Watkins, Dorotinsky, World Bank (2011), Financial Management Information System: 25 Years of World Bank Experience on What Works and What Doesn’t
USAID (2008), Integrated Financial Management Information Systems: A Practical Guide
Khan and Pessoa, IMF (2010), Conceptual Design: A Critical Element of a Government Financial Management Information System Project
http://www.finance.gov.au/cbms/

## Slide 19
Thank you